## Sheet1
Responsibility | Phase
TechM ESD | Assessment | Decision to select 3rd party Solution to select for Patching ->Patch My PC (Estimated cost per year is $21150 for 6500 devices ($3.50 per device per year)( ->Ivanti Patch for Endpoint Manager(Estimated cost per year is £28860 for 6500 devices (£4.44 per device)) ->Flexera Patch Automation for SVM (Estimated cost for 3 years is £140000 (approx. £46000 per year) (£7.07 per device per year)) ->Windows Store (Winget)(Free)
TechM ESD |  | Application Scope for POC Adobe Acrobat Reader\Reader DC Google Chrome Mozilla Firefox (en-us) Notepad++ (64-bit)
TechM ESD |  | Device Scope for POC 100 device per application
TechM ESD |  | Testing Management Solution = Intune and SCCM both
TechM ESD |  | Success Criteria - More then 90% compliance
TechM ESD |  | Demo session from the vendor(Patch My PC)
TechM AD/AAD team | Implementation and testing | App registrations in Azure
TechM ESD |  | Install and configure Patch My PC( require assistance from PmP to step)
TechM ESD |  | Generate a device list having scope application installed (100 Device /Application)
TechM ESD |  | Capture current application version status from SCCM reports
Client |  | Client will select and provide 100 devices for each app
TechM ESD |  | Create 2 Device Group in Intune (Adobe Acrobat Reader\Reader DC ,Google Chrome )
TechM ESD |  | Create 2 Device based Collections in SCCM (Notepad++ (64-bit) ,Google Chrome )
TechM ESD |  | Sync scoped Apps in SCCM and Intune
TechM ESD |  | Create Deployment from Intune for scoped application
TechM ESD |  | Create Deployment from SCCM for scoped application
TechM ESD |  | Perform Internal testing and share results
TechM ESD |  | Perform UAT and share result
Client |  | Take approval to deploy in rest of the scoped devices
TechM ESD |  | Full deployment to each of the devices in scope through SCCM\Intune (100 devices)
TechM ESD |  | Share compliance status of online devices
TechM ESD |  | Roll-back at end of Proof of Concept
TechM ESD |  | Removal of Patch My PC component installed
TechM ESD |  | Cleanup of app registrations
TechM ESD |  | Cleanup for groups created for devices\deployments
Client | GO /no GO decision