## Upgrade Plan
S# | Plan/Activity | Date | Completed
1 | Change (CR) to be initiated on 5th June and have it approved from Client | 5th June, 2024 | Done
2 | Create a Request Task for Matt Quin to take Server Snapshot (DC1MECM01P & DC1SQL7005P) | 7th June, 2024 | Done
3 | Check list Configuration Manager Upgrade 2309 | 5th June, 2024 | Done
4 | ADK has to be upgraded (\\tord2860\d$\ADK) Compatiblity tested with 2309 | 6th June, 2024 | Not Needed
5 | Upgrade MDT | 6th June, 2024 | Not Needed
6 | Back-up Old Boot image / If ADK is upgraded | 6th June, 2024 | Not Needed
7 | Disable all site maintenance tasks at each site for the duration of that site's upgrade. | 7th June, 2024 | Done
8 | Verify server snapshot / SCCM backup | 7th June, 2024 | Done
9 | Download prerequisite files and redistributable files. | 7th June, 2024 | Done
10 | Test DBUpgrade | 7th June, 2024 | Not Needed
11 | Close any open SCCM consoles | 7th June, 2024 | Done
12 | Inplace upgrade of ConfigMgr 2309 | 7th June, 2024 | Done
14 | Verify Installation success | 7th June, 2024 | Done
15 | Upgrade SCCM clients to newer version. | 7th June, 2024 | Done
16 | Enable back the Site maintenances that we disable before upgrade | 7th June, 2024 | Done
Complete SCCM 2107 Upgrade Guide - Prajwal Desai
MDT Upgrade link: | https://www.microsoft.com/en-us/download/details.aspx?id=54259

## Maintenence Task
Task Name | By Default Status before upgrade | Schedule start after | Schedule start before | Schedule day | Last start time | Last completion time | Success | Site Code
Backup Site Server | Yes | 2:00 | 5:00 | Tue, Fri | 2024-06-07 02:00 | 2024-06-07 02:00 | Yes | P02
Check Application Title with Inventory Information | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:35 | 2024-06-01 00:37 | Yes | P02
Clear Install Flag | No | 0:00 | 5:00 | Sun |  |  |  | P02
Delete Aged Application Request Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:30 | 2024-06-01 00:30 | Yes | P02
Delete Aged Client Download History | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Aged Client Operations | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:05 | 2024-06-07 00:05 | Yes | P02
Delete Aged Client Presence History | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:10 | 2024-06-07 00:10 | Yes | P02
Delete Aged Cloud Management Gateway Traffic Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:40 | 2024-06-01 00:40 | Yes | P02
Delete Aged CMPivot Results | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Aged Collected Diagnostic Files | Yes | 0:00 | 5:00 | Sun | 2024-06-02 00:10 | 2024-06-02 00:10 | Yes | P02
Delete Aged Collected Files | Yes | 0:00 | 5:00 | Sat | 2024-06-01 | 2024-06-01 00:06 | Yes | P02
Delete Aged Computer Association Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:15 | 2024-06-01 00:16 | Yes | P02
Delete Aged Console Connection Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:10 | 2024-06-07 00:10 | Yes | P02
Delete Aged Delete Detection Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Aged Device Wipe Record | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:25 | 2024-06-01 00:25 | Yes | P02
Delete Aged Devices Managed by the Exchange Server Connector | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:10 | 2024-06-01 00:10 | Yes | P02
Delete Aged Discovery Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:20 | 2024-06-01 00:45 | Yes | P02
Delete Aged Distribution Point Usage Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:15 | 2024-06-07 00:15 | Yes | P02
Delete Aged Endpoint Protection Health Status History Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:15 | 2024-06-01 00:15 | Yes | P02
Delete Aged Enrolled Devices | No | 0:00 | 5:00 | Sat |  |  |  | P02
Delete Aged Inventory History | Yes | 0:00 | 5:00 | Sat | 2024-06-01 | 2024-06-01 00:25 | Yes | P02
Delete Aged Log Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Aged Notification Task History | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:10 | 2024-06-07 00:10 | Yes | P02
Delete Aged Passcode Records | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:15 | 2024-06-07 00:15 | Yes | P02
Delete Aged Replication Summary Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:10 | 2024-06-07 00:10 | Yes | P02
Delete Aged Replication Tracking Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:05 | 2024-06-07 00:05 | Yes | P02
Delete Aged Scenario Health History | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:15 | 2024-06-01 00:16 | Yes | P02
Delete Aged Software Metering Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:15 | 2024-06-07 00:15 | Yes | P02
Delete Aged Software Metering Summary Data | Yes | 0:00 | 5:00 | Sun | 2024-06-02 00:05 | 2024-06-02 00:05 | Yes | P02
Delete Aged Status Messages | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Aged Threat Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:40 | 2024-06-01 00:40 | Yes | P02
Delete Aged Unknown Computers | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:30 | 2024-06-01 00:30 | Yes | P02
Delete Aged User Device Affinity Data | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:50 | 2024-06-01 00:50 | Yes | P02
Delete Expired MDM Bulk Enroll Package Records | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:35 | 2024-06-01 00:35 | Yes | P02
Delete Inactive Client Discovery Data | No | 0:00 | 5:00 | Sat |  |  |  | P02
Delete Obsolete Alerts | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Delete Obsolete Client Discovery Data | No | 0:00 | 5:00 | Sat |  |  |  | P02
Delete Obsolete Forest Discovery Sites And Subnets | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:50 | 2024-06-01 00:50 | Yes | P02
Delete Orphaned Client Deployment State Records | Yes | 0:00 | 5:00 | Sat | 2024-06-01 00:05 | 2024-06-01 00:05 | Yes | P02
Delete Unused Application Revisions | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:15 | 2024-06-07 00:15 | Yes | P02
Monitor Keys | Yes | 0:00 | 5:00 | Sun | 2024-06-02 00:20 | 2024-06-02 00:20 | Yes | P02
Rebuild Indexes | No | 0:00 | 5:00 | Sun |  |  |  | P02
Summarize Installed Software Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Summarize Software Metering File Usage Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:05 | 2024-06-07 00:05 | Yes | P02
Summarize Software Metering Monthly Usage Data | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 | 2024-06-07 | Yes | P02
Update Application Available Targeting | Yes | 0:00 | 5:00 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-07 00:05 | 2024-06-07 00:05 | Yes | P02
Update Application Catalog Tables | Yes | 0:00 | 23:59 | Sun, Mon, Tue, Wed, Thu, Fri, Sat | 2024-06-06 20:29 | 2024-06-06 20:29 | Yes | P02